## Sheet1
2001 |  |  |  |  | 2002 | [11 empty] | 2003
Aug. | Sep. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | Apr. | May | June | July | Aug. | Sep. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | Apr.
Analysis and Documentation of Privacy Regulations
Develop and Deliver Educational Presentations to Internal Departments
|  |  |  | Develop Questionnaire | Identify and Educate Users |  | Users Complete Questionnaire | Analyze Responses
[5 empty] | Conduct Current State and Gap Analysis | [6 empty] | Finalize Policy on Research
Begin Policy on Research
[5 empty] | Identify Business Associates |  |  | Write Language for Business Associate Contracts |  |  | Execute Business Associate Contracts
[6 empty] | Document Current State of THPs Uses and Disclosures |  |  |  |  | Develop new workflows | Develop Policies & Procedures |  |  | Implement Policies and Procedures & IS Solutions
Conduct Gap Analysis
[7 empty] | Employers Groups/Brokers: Conduct Planning session, identify requirements |  |  | Stakeholders approve recommended approach |  | Develop Policies and Procedures
[12 empty] | Develop Plan & Provide Guidance to Employer Groups |  |  | Execute Business Associate Contract with Self - Insured Groups
[12 empty] | Develop Tracking System for BA's of Employer Groups, Certification of Fully Insured Groups & Authorizations of Individual members |  |  | Obtain Certification from Fully Insured Groups
[9 empty] | Document Marketing Current State |  |  | Develop Policy & Procedure for Marketing
Conduct Gap Analysis
[9 empty] | Evaluate Training Options/Make/Buy Decision |  |  |  |  | Create Curriculum |  |  | Deliver Training
Coordinate the review and approval of all policies and procedures
[7 empty] | Document and Approve Minimum Necessary Requirements | Minimum Necessary Project in Suspension |  |  | Develop Policy for Routine Uses, Disclosures and Requests of PHI | [5 empty] | Monitor Report Changes
[10 empty] | Re-Charter and Re- Forecast Project Plan |  | Develop Policy for Non-Routine Uses, Disclosures and Requests of PHI |  |  | Develop Minimum Necessary Guidelines
[8 empty] | Draft Privacy Notice |  |  | Review and Approve Privacy Notice |  | CMS & DOI Approval |  | Design and Printing |  |  | Mail Privacy Notice